[image: image1.png]



	
	
	



Strengthening Capacity of the Middle Tier Cadre for Teacher Coaching and Mentoring – A Study in Sehore Block, Madhya Pradesh, India (2026)
Scope of Work for

External Agency Hiring
1. Organization Overview

Founded in 2000 on the belief that World Change Starts with Educated Children®, Room to Read develops children’s foundational literacy skills, as well as life skills that promote gender equality. As a leading implementer, Room to Read nurtures these essential skills in children by training and coaching educators, creating quality learning materials and spaces, and strengthening education systems – all while honoring the dignity of every child. We develop and deliver evidence-based materials and approaches directly and with partners. We are a valuable partner of choice for government, other system and program partners as well as investors focused on education. Committed to accelerating learning outcomes for more children, more quickly, Room to Read has benefited children across 29 countries, with more than 17 million children actively benefiting from our programming in 2025 alone. By the end of 2027, we aim to double the number of children and communities we support each year. Room to Read envisions a world free from illiteracy and gender inequality, where all children have room to read, learn and grow. Visit us at www.roomtoread.org.
Room to Read India was established in 2003 and has benefited more than 20 million children. It is currently working directly with 12 state governments (Bihar, Chhattisgarh, Delhi NCR, Himachal Pradesh, Jharkhand, Karnataka, Madhya Pradesh, Maharashtra, Rajasthan, Telangana, Uttarakhand and Uttar Pradesh) to support young children unlock their full potential through education.
2. Teacher Coaching Experiment Model Overview
Supported by Jacobs Foundation, the teacher coaching experiment model in Sehore district of Madhya Pradesh builds on Room to Read’s high-touch implementation (2022-2024) model. While engagement continues at the district level, the current experiment model is in the Sehore block of the district. The model is grounded in the hypothesis that strengthening the capacities of Cluster Academic Coordinators (CACs) as instructional coaches, particularly in (a) classroom observation, (b) data-driven decision-making, (c) mentoring practices, and (d) facilitation of quality review meetings, will lead to more effective teacher support. As frontline academic mentors embedded within the government system, CACs are well-positioned to influence classroom practices. Hence, strengthening their role is expected to reinforce academic support structures, improve teaching practices, effective material usage, and ultimately contribute to better student learning outcomes. 
In addition to building capacities of CACs, the experiment seeks to enhance the role of the District Institute of Education and Training (DIET) officials (also identified as Head Coaches), in leading continuous professional development and academic support. CACs serve as the primary instructional coaches, supported by Room to Read Program Associate (PA). The facilitator works closely with DIET to co-design training modules, deliver quarterly training sessions, and provide ongoing mentoring support. DIET officials also participate in joint school visits and review meetings, reinforcing coaching practices and strengthening the academic support structure at the cluster level. Table 1 below outlines the key activities undertaken as part of the experiment.  
The experiment is implemented across 16 clusters within Sehore block. Each CAC supports around 10–15 schools and their associated schools and teachers. Overall, Sehore block comprises 358 schools, 28 CACs, and about 370 teachers. Additionally, through this experiment 6 DIET faculties are identified as Head Coaches, who in turn supports CACs. 



	

Table 1: Key Activities of the Teacher Coaching Experiment Model

	Activity
	Frequency
	Purpose

	I. Capacity Strengthening of Coaching Cadre

	CAC Training 
	 1/Quarter 
	Strengthen coaches’ capacities in classroom observation, mentoring, data-informed decision-making, and facilitating effective quality review meetings.

	DIET Training 
	 1/Year
	Orient DIET on the objectives of the experimental model, ensuring a shared understanding of the data collection tools, DIET’s roles, and the overall activities.

	Room to Read PA
	 2/Year
	Provide PAs with a program overview, clarify their roles and responsibilities, familiarize them with protocols and SOPs, and build understanding of classroom processes for effective implementation.

	II. Teacher Coaching and Mentoring

	CAC Individual visit 
	15/month 
	On-site teacher coaching and mentoring (classroom observation, spot assessment, coach-teacher conference, etc.)

	CAC-DIET Joint visit 
	12/month
	Joint visits to provide supportive supervision, model best practices, and identify gaps in program understanding and protocol adherence.

	CAC-PA Joint visit 
	10/month
	Joint visits to provide supportive supervision, model best practices, and identify gaps in program understanding and protocol adherence.

	CAC- DIET- PA Joint visit 
	2/month
	PAs will demonstrate coaching of CACs in providing supportive supervision to teachers, enabling DIET to learn and apply this approach in their joint visits with CACs.

	Exposure visit (CACs-DIET) 
	1/quarter 
	Visit and observe a champion CAC’s classroom observation process for learnings.

	III. Additional Support

	Digital nudges (WhatsApp messages) for Teachers 
	 1-2 nudges/week (July-Sept’26)
	Spread awareness about key instructional practices, and effective use of Teacher Learning Materials. 

	Digital nudges (WhatsApp messages) for CACs 
	2/month
	Reinforce learning, strengthen classroom observation practices, and ensure adherence to protocols.

	Cluster Academic meetings (Group coaching) 
	1/month
	Reinforce academic support by CACs, share best practices, and discuss classroom challenges.


3. Study Design 
This section presents the study objectives, methodology, sampling, and study tools to be used to carry out the study. 
3.1 
Study Objectives
The scale study aims to assess the implementation fidelity and effectiveness of the teacher coaching experiment model in Sehore block. The specific objectives of the study are:  

1. Implementation Fidelity: To assess the extent to which coaching and mentoring activities are implemented as designed across the selected block.

2. Teaching Practices and Instructional Quality: To examine how participation in coaching and mentoring influence teachers’ classroom practices and instructional quality. 
3. Stakeholders’ Perspectives: To understand the experiences of teachers and coaches with coaching and mentoring activities, including the perceived benefits and challenges with the coaching and mentoring activities. 
3.2 
Methodology 

The study will adopt a mixed-methods approach. The program activity and output monitoring data will be used (Secondary data) to address first and second objectives. Primary data collection, including classroom instruction observations, will also be conducted to address the second objective. The third objective will be addressed using quantitative and qualitative data from the teachers, coaches, and other relevant stakeholders (Primary data) and will be collected at the end phase of the implementation from a sample of schools. 
3.3 
Sampling 

The study will use random sampling for primary data collection. All 16 clusters in Sehore block will be selected. Within each selected cluster, 2 schools will be randomly sampled, resulting in a total of 32 schools and their teachers (Grade 1 and 2). In addition, all 28 CACs, 6 DIET coaches, 1 DIET Principal, and 3 key project staff from Room to Read will be included in the study. 
3.4 
Study Tools
Six tools will be used for primary data collection. Table 2 presents details of each tool, including the stakeholder, sample, purpose, and suggested administration time.
	Table 2: Details of Study Tools

	Tool Name
	Tool Type
	Stakeholder 
	Sample 
	Suggested Administration Time per Stakeholder

	School and Headteacher Background
	Structured tool
	School Headteacher 
	32
	15-20 mins 

	Teacher Interview*
	Semi-Structured 
	Hindi Language Teacher
	32
	20-30 mins

	Classroom Observation
	Structured tool
	Hindi Language Teacher
	32
	Max 90 mins (depending on the actual instruction time)

	Coaches Interview  
	Semi-Structured
	CACs
	28
	40-60 mins

	Head Coaches Focus Group Discussion (FGD)
	Unstructured (Open-Ended)
	DIET 
	1 (6 DIET in one group)
	40-60 mins

	Principal Interview
	Semi-Structured
	DIET Principal
	1
	20-30 mins

	RtR program staff Interview 
	Semi-Structured
	Project lead 

Program Officer – Field 
Program Officer – Country office
	3
	40-60 Mins

	* Given the multi-grade classroom situation in Sehore, some or many of the early grade teachers in the 32 schools are likely to be teaching both grades 1 and 2 in the same classroom. In case some of the selected schools have separate classrooms and teachers for grades 1 and 2, interviews with Grade 2 teachers and the classroom observations for the same Grade 2 teachers will be conducted for the study.  


4. Role of the Agency 
The study will take place between August 2026 to December 2026. The agency will primarily be engaged in qualitative tools development, tools translations, and data collection (as mentioned in Table 2), which will be conducted in October 2026. This will be followed by data processing, analysis, and report preparation in the subsequent months. The agency is expected to complete the data collection activities in a timely and high-quality manner, in alignment with the overall study timeline (Please refer to Table 4 for more details). The agency is required to undertake the following activities timely:

4.1 Build project understanding 

During the inception phase, the agency representatives will build a comprehensive understanding of the project and teacher coaching experiment model of RtR in Sehore block of Madhya Pradesh. For this, the agency is expected to interact with extensively with key program members of RtR State office, India Country office and Global office. 
4.2 Review of project documents 

During the inception phase, the agency will thoroughly review all the key project documents such as project plan, monitoring tools, monitoring data etc. Secondly, the agency will prepare all qualitative (semi-structured and unstructured) data collection tools as prescribed in Table 2. RtR will provide suggestions, review the tools, etc. during preparation of the tools.    
4.3 Selection of the Data Collectors 
The agency will recruit experienced data collectors and supervisors, requiring a minimum of a graduate degree. Data collectors should have at least 3-4 years of relevant experience in conducting surveys, while supervisors should have a minimum of 4-5 years of experience. Experience with school-based survey, classroom observation and qualitative data collection will be an asset. Proficiency in Hindi is mandatory, and familiarity with the local language or dialect is highly preferred.  Additionally, the agency is required to train about 10–20% more data collectors than the number ultimately needed for fieldwork. This will allow for a competitive selection process to ensure only the most competent data collectors are engaged in the main data collection, and to maintain a pool of trained back-ups in case of attrition or unforeseen circumstances.
 
4.4 Training 
There will be seven days of in-person training in Bhopal or Sehore, which will include one day of field practice with the study tools. The agency will be responsible for conducting the training, with members from Room to Read also present throughout the training. The agency will manage all logistical arrangements for the training of data collectors. During the training, data collectors will be trained in the administration of the study tools (as mentioned in Table 2). 
4.3 Data Collection 
The agency is expected to plan all logistic support required for data collection and ensure that the data collection team arrives at school before the scheduled time. Prior appointments with stakeholders’ interviews must be made. RtR will provide the list of 32 sample schools. The agency will collect data from the samples as mentioned in Tables 2 and undertake the following tasks:
· School and Headteacher Background: RtR will provide a digitized tool to collect background information of school and headteacher. Agency is required to collect data from sample schools.
· Teachers’ Classroom Observation: RtR will provide teachers’ classroom instruction observation tool. Format of the administration (paper or digital) will be decided later during the inception phase after understanding the ground realities. Agency is required to collect data from sample schools. Room to Read will analyze the data and provide the findings with agency. The findings will be used by the agency while developing the study report and presentation. 
· Interviews: Agency will be responsible for developing the semi-structured interview for all the stakeholders listed in Table 2, followed by data collection. RtR will review the tools. With the consent of respondent, the interviews will be recorded in SurveyCTO. Agency will be responsible for providing (a) transcribing the recordings; (b) soft copy of translated transcripts in English in Microsoft Word format, and (c) detailed field notes from each interview in English in Microsoft Word Format. 

· Focus Group Discussions: Agency will develop the tool and conduct focus group discussion with Head Coaches. RtR will review the tool. With the consent of respondents, the discussion will be recorded in SurveyCTO. Agency will be responsible for providing (a) transcribing the recordings; (b) soft copy of translated transcripts in English in Microsoft Word format, and (c) detailed field notes from FGD in English in Microsoft Word Format.  
The agency should take the above methods into account when selecting and training the data collectors and supervisors. The agency will share all the raw data files and cleaned files, transcriptions and filed notes with Room to Read.
4.4 Data Analysis
The agency is expected to analyze: (a) all the project monitoring data to address first and second study objectives and (b) qualitative data (interviews and focus group discussions). Agency will share the analysis plan with RtR RM&E team and mutually agree on the analysis plan before it is finalized. In consultation with RtR, the agency will prepare the report of the analysed data to address the study objected listed in sub-section 3.1 above.
 
4.5 Data Quality Measures 
The agency will be responsible for ensuring data quality measures and monitoring the quality of data being collected and cleaning any inconsistent data with prior approval from Room to Read. These includes coordination with school authorities to secure necessary support for data collection for each site, prior appointment with relevant stakeholders for interviews and group discussion, monitor data collection and conduct data quality checks. Agency should appoint appropriate number of supervisors who will be responsible for data quality. The following data quality measures are mandatory (not limited to) for the agency to undertake: 

· For Classroom Practices Observation
Apart from the above, agency is expected to conduct Inter-Rater Reliability test (IRR) for classroom observations. This will be undertaken during the training and during the data collection. 

· First, during the training, there will demo classroom teacher practices (either by video clip or role play), where all the enumerators will observe the activities and fill the observation formats. The results will be analysed and discussed during the training itself, where key mistakes, points to note, feedback will be undertaken. Based on the results, only the enumerators who passes the threshold of reliability test will be selected to conduct the study. 

· Second, the IRR of classroom observation must take place throughout the actual data collection process. Simultaneous classroom observation by two people (observer and supervisor) must be done as part of IRR. The agency must make sure to cover at least 25% of the classroom observation sample for IRR. The number of classrooms for IRR must be distributed across all observers.  RtR will discuss in detailed about the IRR process with the selected agency.
· For Qualitative Data 
· Agency will check at least 10% of interview record of each one of the data collectors immediately post data collection, for corrective measures to be taken timely. 
· Agency will conduct debriefing sessions throughout the data collection process with the data collectors either through face to face / virtual mode needed to be organized to discuss the data quality issues and feedback of supervisor the performance of data collection team. The agency needs to share the proceedings of each of the debriefing sessions with RtR. Technical members from RtR must also be invited to be part of these debriefing sessions. Agencies should propose a plan for regular debriefing sessions in their technical proposals. 

· Apart from these, the RtR technical staff will randomly observe the teachers’ interviews, classroom observations and will listen to a few recordings, throughout the data collection process and provide feedback, important probes to the enumerators. 
Additionally, the agency must: (a) cooperate with Room to Read’s monitoring staff during the data collection phase, and (b) work with the country monitoring team to cross-verify 100% of the data before submitting it to Room to Read’s country office. Additionally, all assessments/interviews completed below the minimum expected duration must be immediately flagged for quality review.
5. Role of Room to Read
· Room to Read will provide all the relevant documents to undertake the study, such as, program document, permission letters, list of schools, contact details of key people, copy of Room to Read’s Child Protection Policy, etc.  

· Room to Read will provide the digitized tools or paper copy of school and headteacher background and classroom observations in SurveyCTO. The agency will be given restricted access to SurveyCTO to conduct the study.

· Support and supervise the agency in preparation and finalization of the qualitative data collection tools and data analysis plan. 

· The technical team members from Room to Read will support the agency in training the data collectors on data collection tools and its administration.  

· In addition to agency’s supervisors, Room to Read will collaborate and participate in the data verification/data quality measurement process. 

6. Requirements and Evaluation Criteria for Agency Selection
6.1 Round 1: Evaluation of Technical Proposals

· The agency should have at least 5 years of experience in the field of education. Experience with qualitative data collection and classroom observations will be preferred.
· Technical proposals should not be more than 10-12 pages. The technical proposals must be submitted as per the prescribed format in Annex A below.  

· Individual technical proposals will not be accepted for this study.

· The technical proposals will be evaluated based on the following (but not limited to):  (a) experience in Education field/similar domain and conducting similar studies; (b) suggested study team, including data collectors, supervisors, other technical members; along with their qualification and experience; (c) understanding of the scope of work, including data analysis expertise for both quantitative and qualitative data; (d) training and data collection plan; (e) process and steps of data quality assurance, including data quality measures taken during the trainings for selection of the data collectors, data collection monitoring, troubleshooting mechanisms etc; (f) timelines of sub-activities as per main activities listed in Table 4 below. The details of the technical evaluation criteria are given below (Table 3).

	Table 3: Technical evaluation criteria for shortlisting the proposals 

	Sr. No 
	Evaluation Indicators 
	Scoring 

	1. 
	Experience in education field/similar domain and conducting similar studies 
	20

	2. 
	Study team qualification and experience 
	15 

	3. 
	Understanding of the scope of work including data analysis expertise for both quantitative and qualitative data
	30 

	4. 
	Training and data collection plan 
	10 

	5. 
	Process and steps of data quality assurance 
	15 

	6. 
	Timelines of the activities 
	10 

	TOTAL SCORE 
	100 


· Agencies scoring at least 75 out of 100 marks on the technical proposal will be shortlisted for Round 2 (Technical Presentation). 
6.2 Round 2: Technical Presentation

Shortlisted agencies will be invited to deliver a technical presentation (in-person or virtual). Each agency will be allotted 45 minutes:

· 30 minutes for presentation

· 15 minutes for Q&A

Round 2 is intended to gain a better understanding of the agency’s proposed approach, including training and data collection plan, data quality assurance measures, experience with digital data collection, classroom observations and qualitative data collection, team composition, as well as to clarify any points identified during the proposal review. These parameters are aligned with the criteria used for assessing technical proposals. Agencies scoring at least 75% in the technical presentation (Round 2) will be shortlisted for the next stage (final round of selection).  
6.3 Final Selection Process
· All agencies are required to submit technical and financial proposals in separate emails within the specified timeline.

· Financial proposals will be opened only for agencies that qualify after Round 2 (Technical Presentation).

· The final selection will be based on a combined assessment of technical evaluation and financial proposal. 
7. Confidentiality and Ethics  

Room to Read will minimize the collection of Personally Identifiable Information (PII) and take appropriate measures to anonymize data. 
8. Key Deliverables and Timelines for Agency 
	Table 4: Key Deliverables and Timelines for Agency

	Deliverable 
	Description 
	Estimated Timeline 
	Payment Tranches (%) 

	1 
	Submission of Inception Report, including (not limited to): 
· Agency’s understanding of the study includes study objectives, field activities and data collection timelines, data analysis framework, training plan and agenda, etc.  

· Detailed work plan for all the activities as prescribed in the Scope of Work
· Data quality assurance process 

· List of key people (data collectors, supervisors, central team members and their roles etc.) who will be engaged with the study 
	 

By the 3rd week of August’26
	20% 

	2 
	Finalization of Data collection tools, Completion of Training and Launch of Data Collection as prescribed in Scope of Work, including:  

· Final and translated data collection tools (excluding School & Headteacher background and Classroom Observation)
· Completion of training as prescribed in the Scope of Work
· Detailed field plan 
· Duly signed Child Protection Policy by all the field staff including ethical consideration.
	 

By the 4th week of September’26  
	30% 

	3 
	Completion of Data Collection, Submission of Final Data and Data Quality Monitoring Report, including: 
· Daily field work update

· Field work completion report  
· Raw data 
· Qualitative field notes, transcriptions and translated files

· Cleaned data sets (with notes on the cleaning process and Stata do files) 
· Data quality monitoring report 
	By the 4th week of October’26 
	30% 

	   4
	Report and Presentation, including: 
· Data analysis 

· Report writing (at least 2 drafts) 

· Presentation of key findings
 
	 

By the 3rd week of November’26 
	20% 


 

 Annex A 
Technical Proposal Template 
	Technical Proposal

	Content (Maximum page length or range) 
	Details  

	Organization Details 
(1 page max.) 
	· Organization overview, including management structure. 

· Summary of incorporation/legal status. 

	Agency’s Understanding 
(1-2 pages max.) 
	Brief narrative outlining the Agency’s understanding of the proposed activities.  

	Relevant Experience  
(2 pages max.) 
	Summary of relevant project experience focused on the following:   
1. Experience in conducting similar studies.  

· Recruitment and supervision of well-qualified data collectors.  

· Enumerator training design and delivery.  

2. Experience in tablet-based data collection using SurveyCTO.  

· Securing access to schools for data collection in a timely and appropriate manner; and  

· Data Management & Cleaning 

Project Summaries for up to 5 most relevant assignments in last 3 years should be included at the end of this section. 

	Comments and Suggestions 
(1-page max.) 
	List of observations or suggestions (if any) on the RFP and scope of work.  

	Technical Approach and Workplan (3-4 pages max.) 
	Description of the Approach and Workplan proposed by the agency for successful execution of the activities listed in the RFP.  More specifically:  
3. Approach to collaborate with Room to Read on data collection planning and preparation. 

4. Approach to fielding data collection at the schools, while ensuring minimal disruption and maximum time and efficiency. 

·  Approach to classroom observations, qualitative data collection and analysis. 
· Approach to recruiting and retaining sufficiently qualified data collectors. 

· Approach to ensuring data quality, protection of data and PII and compliance with relevant respondent protection protocols. 

· Approach to identifying, communicating, and addressing barriers during planning and implementation of data collection.  

· Anticipated challenges for the above activities. 

· Risk mitigation strategies for the above activities. 
· A week-wise Gantt Chart summarizing the project plan with deliverables should be included at the end of this section 

	Project Staffing and Management Plan 
(1-2 pages max.) 
	Identify the project staffing plan and structure, essential staffing, and the percentage of the time each will spend on the activities listed in RFP:    
· Agencies should describe the proposed team structure in this section. 

· Agencies should clearly specify their proposed training and data collection staffing plan, including oversight/supervisory structures. 

· Agencies should include summary profiles of all candidates considered essential in this section. 

· Please include a resume for everyone considered essential for the successful implementation of this contract in the annex as per the specified format. 


Annex B 
Financial Proposal Template 
	Financial Proposal  

	Budget Narrative  
	Narrative summary of the proposed budget including discussion and rationale for costing approach, major expenses, risks, and other considerations related to the budget.

	Financial Proposal Details  
	The proposed budget and associated narrative will have sufficient detail to allow for a detailed evaluation of the costs proposed, using the Budget Template attached along with the RFP. Budgets should be submitted in Indian Rupees. Room to Read reserves the right to request any additional information to support the proposed budget. 


	<NAME OF FIRM>
	 
	 
	 
	 
	 

	
	
	
	
	
	

	Agency should carefully review this template and add any line items they feel necessary to complete the activities outlined in the RFP. 

	Cost Heads and Items
	Unit Cost
	 Persons/ Teams/ Units 
	 Days 
	Total Units
	Cost in INR 

	Labor (illustrative positions, please update according to your proposed plan)
	 
	 
	 
	 
	 

	Survey Manager/Trainer
	<Insert daily rate>
	 
	 
	 
	 

	Field Coordinator/Trainer
	<Insert daily rate>
	 
	 
	 
	 

	Data Manager 
	<Insert daily rate>
	 
	 
	 
	 

	Supervisors - Training + Field Work
	<Insert daily rate>
	 
	 
	 
	 

	Data Collectors - Training + Field Work
	<Insert daily rate>
	 
	 
	 
	 

	Programmer 
	<Insert daily rate>
	 
	 
	 
	 

	Analyst and Report Writer
	<Insert daily rate>
	 
	 
	 
	 

	Tools development 
	<Insert daily rate>
	 
	 
	 
	 

	Other...
	<Insert daily rate>
	 
	 
	 
	 

	Subtotal Labor
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	Travel and Other Direct Costs
	 
	 
	 
	 
	 

	Training
	 
	 
	 
	 
	 

	Training Materials & Printing of Tools/Manuals (per person)
	 
	 
	 
	 
	 

	Training Facility Rental (rooms/day)
	 
	 
	 
	 
	 

	Transportation to/from training facility, if required (person/day)
	 
	 
	 
	 
	 

	Accommodation, if required for out-of-town enumerators (persons/day)
	 
	 
	 
	 
	 

	Lunch & Coffee Breaks during Field Staff Training (person/day)
	 
	 
	 
	 
	 

	Document Translations - for training purposes only (if any)
	 
	 
	 
	 
	 

	Other...
	 
	 
	 
	 
	 

	Other...
	 
	 
	 
	 
	 

	Subtotal Training
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	Survey Administration
	 
	 
	 
	 
	 

	Field Staff Equipment (ID cards, etc; per person)
	 
	 
	 
	 
	 

	Transportation for team (team/day)
	 
	 
	 
	 
	 

	Meal Allowance for Supervisors and Data Collectors (per person per day)
	 
	 
	 
	 
	 

	Accommodation for Supervisors and Data Collectors (per person per day)
	 
	 
	 
	 
	 

	Communications Allowance (per person)
	 
	 
	 
	 
	 

	Meal Allowance for Field Management (per person per day)
	 
	 
	 
	 
	 

	Accommodation for Field Management (per person per day)
	 
	 
	 
	 
	 

	Transportation for Field Management (per car per day)
	 
	 
	 
	 
	 

	Tablet rental (with GPS and WiFi capability) 
	 
	 
	 
	 
	 

	Document Translations - for survey administration purposes only (if any)
	 
	 
	 
	 
	 

	Other...
	 
	 
	 
	 
	 

	Other...
	 
	 
	 
	 
	 

	Subtotal Survey Administration 
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	TOTAL COST (not including GST)
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	GST
	 
	 
	 
	 
	 

	 
	 
	 
	 
	 
	 

	TOTAL COST (including GST)
	 
	 
	 
	 
	 


HOW TO APPLY 

Proposals are invited from the interested agency for the above assignment and the last date for receiving the proposal is 15th June 2026 at procurement.india@roomtoread.org  [do not copy anyone from RtR] 

Kindly submit two separate emails with the following subject lines:  
o EMAIL (1): TECHNICAL PROPOSAL – TCM Study, Sehore (MP) 2026
o EMAIL (2): FINANCIAL PROPOSAL – TCM Study, Sehore (MP) 2026
Submission terms:  

· All agencies are advised to thoroughly review the SoW ToR before applying. 

· Technical and Financial proposals are to be shared in two different emails separately and not in a single email (mandatory) 
· Incomplete applications or deviations from the prescribed process will result in automatic rejection. 
 

· Proposals received after the prescribed deadline will not be considered.  

· Only shortlisted agencies will be contacted and may be requested for face-to-face/online interaction/presentation.  

For queries, please contact: 

Vinod Kandwal
Vinod.Kandwal@roomtoread.org  

1
[image: image1.png]
 PAGE 
2

[image: image2.png]


