PLAN INTERNATIONAL (INDIA CHAPTER)

REQUEST FOR QUOTATION (RFQ)

Development of Multi-Sport Courts (Basketball, Volleyball & Badminton)

Comprehensive School Improvement Program (CSIP), Bengaluru.
RFQ Reference No.: PI/CSIP/SPORTS/BLR/2026/0010
Issue Date: 06 November 2026

Procurement Method: Normal/RFP
Evaluation Methodology: Quality and Cost Based Selection (QCBS 70:30)

PART I – ABOUT PLAN INTERNATIONAL (INDIA CHAPTER)

Plan International (India Chapter), commonly referred to as Plan India, is an Indian registered not-for-profit organization striving to advance the welfare and development of children and equality for girls and women. Through child-centred community development approaches, Plan India seeks to create lasting impact in the lives of vulnerable children, their families and communities.

Since 1996, Plan India has improved the lives of millions of children and young people by enabling access to quality education, child protection, healthcare services, healthy environments, livelihood opportunities and participation in community development.

PART II – PROJECT BACKGROUND

The Comprehensive School Improvement Program (CSIP), Bengaluru aims to strengthen educational and recreational infrastructure in Government Schools.

Under this project, Plan International (India Chapter) intends to establish Multi-Sport Courts comprising Basketball, Volleyball and Badminton facilities in the following schools:

1. Government Girls High School (GGHS), Ramanagara

2. Karnataka Public School (KPS), Padarahalli

3. Karnataka Public School (KPS), Jalamangala

The intervention includes development of sports courts, ground preparation, civil works, installation of sports flooring, court markings, basketball systems, volleyball and badminton systems, interlocking works and associated infrastructure as detailed in the attached BOQs.

PART III – OBJECTIVES OF THE ASSIGNMENT

The selected bidder shall:

1. Develop and operationalize Multi-Sport Courts in the identified schools.

2. Promote participation of children, especially girls, in sports activities.

3. Improve access to safe, inclusive and child-friendly sports infrastructure.

4. Complete all civil works, sports flooring and equipment installation.

5. Hand over fully functional sports facilities within the stipulated timeline.

PART IV – SCHOOL LOCATIONS

	Sl. No.
	School Name
	Location

	1
	GGHS Ramanagara
	Ramanagara, Karnataka

	2
	KPS Padarahalli
	Ramanagara, Karnataka

	3
	KPS Jalamangala
	Ramanagara, Karnataka


PART V – PROCUREMENT SCHEDULE

	Sl. No.
	Description
	Schedule

	1
	Date of Issuance of RFQ
	06 Nov 2026 (Friday)

	2
	Pre-Bid Meeting (Virtual through Microsoft Teams)
	10 Nov 2026 (Tuesday), 11:00 AM

	3
	Last Date & Time for Submission of Clarification Requests
	10 Nov 2026 (Tuesday), 05:00 PM

	4
	Issuance of Clarifications/Addendum (if any)
	11 Nov 2026 (Wednesday)

	5
	Site Visit by Interested Bidders (Strongly Encouraged)
	11–12 Nov 2026

	6
	Last Date & Time for Submission of Technical and Financial Proposals
	13 Nov 2026 (Friday), 12:00 Noon

	7
	Opening of Technical Proposals 
	13 Nov 2026 (Friday), 03:00 PM

	8
	Technical Evaluation
	16–17 Nov 2026

	9
	Opening of Financial Proposals of Technically Qualified Bidders
	18 Nov 2026 (Wednesday)

	10
	Due Diligence / Reference Verification
	18 Nov 2026

	11
	Issue of Purchase Order / Letter of Award
	19 Nov 2026

	12
	Contract Finalization and Kick-Off Meeting
	20 Nov 2026


Important Notes

a) A Tender Box shall be placed at the Reception Area of Plan International (India Chapter), New Delhi Office.

b) Bidders shall submit Technical and Financial Proposals in two separate sealed envelopes enclosed within one outer sealed envelope.

c) The outer envelope shall clearly mention:

· RFQ Reference Number

· Name of Assignment

· Name and Address of Bidder

d) The Tender Box shall close at 12:00 Noon on 13 November 2026. Late submissions shall not be considered.

e) Plan International (India Chapter) reserves the right to amend the procurement schedule through written corrigendum/addendum.

f) Plan International (India Chapter) reserves the right to award the contract in whole or in part, or to split the scope among multiple qualified bidders if considered necessary in the interest of implementation, delivery timelines, risk mitigation or value for money.

PART VI – LETTER OF INVITATION

Plan International (India Chapter) invites sealed proposals from eligible contractors, sports infrastructure agencies, civil contractors and infrastructure development firms for:

Development of Multi-Sport Courts (Basketball, Volleyball & Badminton) under CSIP Bengaluru Project

Clarifications may be sought through: procurement@planindia.org
PART VII – INSTRUCTIONS TO BIDDERS

1. Submission of a proposal constitutes acceptance of all terms and conditions contained in this RFQ.

2. Any amendment or clarification shall be valid only if issued in writing by Plan India.

3. Partial, incomplete or conditional bids may be rejected.

4. Financial Proposal and BOQ shall be duly signed and stamped.

5. Proposal validity shall be 90 Calendar Days from the bid submission deadline.

6. Participation is restricted to legally registered entities with relevant experience.

7. NGOs are not eligible to participate.

8. Plan India maintains a zero-tolerance policy towards fraud, corruption, collusion, conflict of interest and safeguarding violations.

9. All costs associated with proposal preparation and submission shall be borne solely by the bidder.

10. Submission of false or misleading information may result in disqualification.

11. Bidders shall be deemed to have satisfied themselves regarding site conditions before submission of bids.

PART VIII – CONTENTS OF PROPOSALS
Envelope A – Technical Proposal

The Technical Proposal shall contain:

1. Bidder Information Form

2. Certificate of Registration/Incorporation

3. PAN Card

4. GST Registration Certificate

5. Company Profile

6. CA Certified Average Annual Turnover Certificate (Last Three Financial Years)

7. Audited Financial Statements (Last Three Financial Years)

8. Similar Project Experience

9. Work Orders and Completion Certificates

10. Technical Methodology and Work Plan

Envelope B – Financial Proposal

The Financial Proposal shall contain:

1. Duly Filled BOQs

2. Commercial Summary

3. GST Break-Up

No technical information shall be included in the Financial Proposal.
PART IX – BID SUBMISSION INSTRUCTIONS

Submission Method

The bidder shall submit:

· Envelope A – Technical Proposal

· Envelope B – Financial Proposal

in two separate sealed envelopes, enclosed in one outer sealed envelope.

Superscription on Outer Envelope

FAST-TRACK RESTRICTED RFQ FOR DEVELOPMENT OF MULTI-SPORT COURTS UNDER CSIP BENGALURU PROJECT
RFQ Ref. No.: PI/CSIP/SPORTS/BLR/2026/0010
Name and Address of Bidder

Bid Submission Location

Tender Box
Procurement Department
Plan International (India Chapter)
1 Community Centre, Zamrudpur
Kailash Colony Extension
New Delhi – 110048

Bid Submission Deadline

13 November 2026 (Friday), 12:00 Noon IST
Late bids shall not be accepted.

Only financial proposals of technically qualified bidders shall be opened.

PART X – ELIGIBILITY CRITERIA

The bidder shall:

1. Be legally registered in India.

2. Possess valid PAN and GST registrations.

3. Have successfully completed at least three similar assignments within the last five years.

4. Submit relevant work orders and completion certificates.

5. Submit CA-Certified Average Annual Turnover Certificate for the last three financial years.

6. Submit Audited Financial Statements for the last three financial years.

7. Not be blacklisted by any Government Agency, PSU, Donor Agency or International Organization.

PART XI – SCOPE OF WORK

Civil Works

· Site clearance and debris removal.

· Ground leveling, grading, filling and compaction.

· Earthwork and foundation preparation.

· PCC and concrete court construction.

· Surface drainage arrangements.

· Interlocking and allied development works.

Playing Surface

· Supply and installation of UV-stabilized PP Modular Sports Flooring or approved equivalent as specified in BOQ.

· Installation of edge tiles and ramps.

· Multi-sport court markings.

Sports Equipment

· Basketball Pole System, Backboard, Ring and Net.

· Volleyball Pole and Net System.

· Badminton Pole and Net System.

· All fixtures, foundations and accessories.

Completion & Handover

· Inspection and testing.

· Rectification of defects.

· Completion Report.

· Before and After Photographs.

· Joint Inspection Report.

· School Acceptance Certificate.

· Handover Documentation.

PART XII – TECHNICAL SPECIFICATIONS

Detailed specifications, dimensions, workmanship requirements and quantities shall be governed by the attached BOQs.

At a minimum:

Sports Flooring

· UV-Stabilized PP Modular Sports Tiles.

· Weather-resistant.

· Anti-skid finish.

· Shock-absorbing design.

Basketball System

· Heavy-duty outdoor basketball poles.

· Powder-coated GI/MS structure.

· FRP or Tempered Glass Backboard.

· Standard basketball ring and net.

Volleyball & Badminton Systems

· GI/MS powder-coated poles.

· Competition grade nets.

· Outdoor weather-resistant fittings.

Civil Works

· Proper ground compaction and leveling.

· Concrete base and foundations.

· Adequate drainage arrangements.

· Durable outdoor finishing.

Precedence Clause

In the event of any discrepancy between this RFQ and the School-wise BOQs, the technical specifications and requirements provided in the approved BOQs shall prevail for execution purposes.

PART XIII – BILL OF QUANTITIES (BOQ)

· Annexure I – GGHS Ramanagara

· Annexure II – KPS Padarahalli

· Annexure III – KPS Jalamangala
· Anexxure IV -Material Specifications for each schools
The BOQs form an integral part of this RFQ.
PART XIV – TECHNICAL EVALUATION

	Criteria
	Marks

	Similar Sports Infrastructure Experience
	25

	Technical Compliance with Specifications & BOQ
	20

	Warranty & Post-Completion Support
	20

	Methodology & Work Plan
	15

	Government School / CSR Project Experience
	10

	Team Strength & Execution Capability
	5

	Implementation Timeline & Deployment Plan
	5

	Total
	100


Minimum Technical Qualification Score: 70 Marks
PART XV – QCBS EVALUATION

	Component
	Weightage

	Technical Proposal
	70%

	Financial Proposal
	30%

	Total
	100%


PART XVI – FINANCIAL EVALUATION

Financial Score:

Fs = (L1 ÷ Fx) × 30
Where:

· Fs = Financial Score

· L1 = Lowest Evaluated Price

· Fx = Financial Price under Evaluation

Maximum Financial Score: 30 Marks
PART XVIII – FINAL SCORE

Final Combined Score = Technical Score (70) + Financial Score (30)
The bidder obtaining the highest combined score shall be recommended for award.

PART XIX – PAYMENT TERMS

	Milestone
	Payment

	Mobilization and Site Commencement
	On mutual agreement with Plan India

	Completion of Ground Preparation, Civil Works and Flooring Installation
	

	Completion of Equipment Installation and Joint Inspection
	

	Final Acceptance and Handover
	


Applicable taxes and statutory deductions shall apply.
PART XX – WARRANTY REQUIREMENTS

1. Minimum 12-Month Defect Liability Period.

2. Defect Liability Period shall commence from the date of final handover and acceptance.

3. Rectification of workmanship defects during the defect liability period.

4. Repair or replacement of defective materials at no additional cost.

5. Warranty support throughout the defect liability period.

PART XXI – SAFEGUARDING POLICY

The successful bidder shall comply with Plan International (India Chapter)'s Safeguarding Policy.

All personnel deployed under this assignment shall adhere to safeguarding requirements applicable to child-centred environments and may be required to undergo safeguarding orientation.

Level of Contact: Direct – Level A
PART XXII – GENERAL TERMS AND CONDITIONS

1. Plan International (India Chapter) reserves the right to accept or reject any or all bids without assigning any reason.
2. Plan International (India Chapter) may cancel, suspend, amend or re-issue the procurement process at any stage.

3. The successful bidder shall obtain and maintain all approvals, permits, registrations and licenses required for execution.

4. The bidder shall comply with all applicable labour laws, safety regulations and statutory requirements.

5. The successful bidder shall be solely responsible for safety at site.

6. No subcontracting shall be permitted without prior written approval of Plan India.

7. Any attempt to influence the evaluation process may result in disqualification.

8. Bidders shall disclose any conflict of interest.

9. Fraud, corruption, collusion or safeguarding violations may result in disqualification and contract termination.

Limitation of Liability

Plan International (India Chapter) shall not be liable for any costs incurred by bidders in preparation and submission of proposals or participation in the procurement process.

PART XXIII – FORCE MAJEURE

Neither party shall be liable for failure to perform obligations due to events beyond reasonable control including natural disasters, floods, earthquakes, pandemic, epidemic, acts of government, civil unrest, war, labour strikes or other force majeure events.

PART XXIV – TERMINATION

Plan International (India Chapter) may terminate the contract by written notice if:

· The contractor commits a material breach of contract.

· Agreed timelines are repeatedly missed.

· Work quality is unsatisfactory.

· Fraud, corruption or safeguarding violations are identified.

· Insolvency, bankruptcy or liquidation proceedings are initiated against the contractor.

PART XXV – CONTRACT AWARD

1. The contract shall be awarded to the bidder obtaining the highest combined QCBS score and meeting all technical, commercial and compliance requirements.

2. Plan India reserves the right to negotiate technical and commercial aspects before award.

3. The contract may be awarded to one bidder or split among multiple qualified bidders (ratio of contract to bidders, shall be on discretion of PII).
4. Issuance of a Purchase Order or Letter of Award shall constitute formal award.
5. Plan International (India Chapter) reserves the right to split the contract
PART XXVI – FINANCIAL BID FORMAT

Financial proposals shall be submitted against:

· Annexure I – GGHS Ramanagara BOQ

· Annexure II – KPS Padarahalli BOQ

· Annexure III – KPS Jalamangala BOQ

All rates shall be quoted in INR.

GST shall be indicated separately.

Commercial Summary

	Particulars
	Amount (INR)

	Total Cost (Excluding GST)
	

	GST
	

	Grand Total (Including GST)
	


PART XXVII – ANNEXURES

· Annexure I – Detailed BOQ, GGHS Ramanagara

· Annexure II – Detailed BOQ, KPS Padarahalli

· Annexure III – Detailed BOQ, KPS Jalamangala

· Annexure IV – Bidder Information Form

· Annexure V – Financial Proposal Format

· Annexure VI – Declaration of Non-Blacklisting

· Annexure VII – Conflict of Interest Declaration

· Annexure VIII – Safeguarding Declaration

ISSUED BY

Procurement Department
Plan International (India Chapter)
1 Community Centre, Zamrudpur
Kailash Colony Extension
New Delhi – 110048, Email: procurement@planindia.org
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MATERIAL SPECIFICATION REPORT 


Development of Multi-Sport Courts – GGHS Ramanagara, KPS Jalamangala & KPS 
Padarahalli, Bengaluru 


Comprehensive School Improvement Program (Model School Project) – Bengaluru  


 


1. Purpose 


This report provides recommended material specifications and indicative brands / manufacturers for the 
multi-sport courts (basketball, volleyball and badminton) proposed at GGHS Ramanagara, KPS 
Jalamangala and KPS Padarahalli, Bengaluru. The recommendations are aligned with the attached 
BOQ / estimate and the layout drawings MSC-01 and MSC-02 (Rev A), and are intended to ensure 
durability, safety, ease of maintenance and availability through the Bengaluru / Ramanagara market. 
Equivalent or superior products may be accepted subject to prior approval and submission of technical 
data / warranty. 


2. Project Scope 


School Name Court Size Area Perimeter (edge tiles) 


GGHS Ramanagara 70 ft × 30 ft 2,100 sq ft 200 rft 


KPS Jalamangala 70 ft × 30 ft 2,100 sq ft 200 rft 


KPS Padarahalli 70 ft × 30 ft 2,100 sq ft 200 rft 


Total (3 schools) – 6,300 sq ft 600 rft 


 


All three schools have the same court size and the same layout (Drg. MSC-01), so one specification 
applies to all. The court is a combined multi-sport surface of interlocking PP tiles on a cemented base, 
with the following markings: 


Game Marked court size Line width / 
colour 


Remarks 


Basketball (reduced) 20,336 × 8,144 mm 50 mm, white Centre circle R1,200; two lanes 3,600 × 
3,600; two arcs R1,800. 


Volleyball 15,000 × 7,500 mm 50 mm, yellow Net at centre line; attack lines 2,500 
mm from net. 


Badminton (doubles) 13,400 × 6,100 mm 40 mm, sky-blue Singles sides, short and long service 
lines, centre lines. 


 


Quantities per school, as per the estimate: 


Item (per school) Quantity Unit Reference 


Site clearance and levelling 2,100 sq ft Estimate item 1.1 


Cemented court base (sub-base, PCC, 
CC) 


2,100 sq ft Estimate item 1.2 


PP modular interlocking sports tiles 2,100 sq ft Estimate item 2.1 


PP edge / side tiles 200 rft Estimate item 2.2 


Court line marking (3 games) 1 LS Estimate item 2.3 


Basketball hoop poles with backboard and 
ring 


1 pair Estimate item 3.1 


Volleyball-cum-badminton post system 
with nets 


1 set Estimate item 3.2 
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3. Recommended Material & Brand Specifications 


Sr. Material / Work 
Item 


Minimum Recommended 
Specification 


Preferred Brand / 
Manufacturer 


Notes 


1 Cement OPC 43 / 53 grade (IS 269) or PPC 
(IS 1489); fresh, genuine, in sealed 
bags, batch-tested. Used for sub-base 
blinding, PCC 1:2:4 (~M15), CC 1:2:4 
top layer and M20 foundation blocks / 
collars. 


UltraTech / ACC / 
Ambuja 


Use one approved 
brand consistently for 
the major concrete 
works. Store off the 
ground, dry; no lumpy 
or damp stock. 


2 Coarse 
aggregate 


Clean crushed hard-stone aggregate, 
well graded, free from clay, organic 
and deleterious matter. 20 mm graded 
for PCC and M20 concrete; 12 mm 
graded for the CC top layer. 


Approved local 
crusher supplier 
(Ramanagara / 
Bengaluru) 


Source and grading to 
be approved before 
bulk supply. 


3 Fine aggregate 
/ sand 


Clean, well-graded Zone II sand 
(natural or manufactured sand), free 
from silt, clay and organic matter, 
suitable for concrete (IS 383). Crusher 
dust / coarse sand for blinding the 
sub-base. 


Approved local 
supplier 


Test / approve the 
source before bulk 
supply. 


4 Brick ballast / 
stone sub-base 


75 mm thick compacted layer of 40 
mm nominal size WELL-BURNT brick 
ballast (or hard stone ballast), free of 
clay and organic matter. Unburnt 
(kacchi) brick not permitted. Blinded 
with crusher dust / coarse sand, 
watered and rolled to refusal; surface 
within ±10 mm. 


Approved local 
supplier 


No soft, over-burnt or 
contaminated material. 
Compact in layers. 


5 PCC base PCC 1:2:4 (cement : Zone II sand : 20 
mm graded aggregate by volume, 
approx. M15), 75 mm thick, laid to line 
and level between edge forms, 
compacted and wet-cured for 7 days. 


Site-batched with 
approved cement / 
aggregate 


Final mix and 
thickness per 
approved drawing 
(MSC-02) and 
Engineer-in-charge. 


6 Top CC layer CC 1:2:4, 50 mm thick, 12 mm graded 
aggregate, screeded and steel-
trowelled to a smooth uniform finish. 
Surface fall 1 in 120 (about 0.5 in per 
10 ft) across the width towards the 
drain; flatness ±3 mm under a 3 m 
straight-edge; contraction joints at not 
more than 4 m c/c; edges finished true 
to receive edge tiles; wet-cured 7 
days. 


Approved cement / 
aggregate 


Edge shuttering true to 
line and level. Tile 
surface to finish flush 
with, and not more 
than 25 mm above, 
surrounding ground. 


7 Outdoor sports 
tiles 


Interlocking polypropylene (PP) 
modular tiles: virgin UV-stabilised PP 
copolymer (no recycled content); 
square modules 250–310 mm; 
thickness not less than 13 mm; anti-
skid textured top; open-grid drainage; 
four-side interlock; loose-laid and 
interlocked on the cured CC layer. 
Colours: blue field, green volleyball 
zone, red free-throw lanes (to be 
confirmed). Minimum 3-year 
manufacturer warranty. 


FitFlex / equivalent 
approved make 


Preferred surface for 
school multi-sport use. 
Submit sample, 
datasheet, test reports 
and warranty before 
purchase. 


8 Edge / ramp 
tiles 


Matching bevelled edge (ramp) tiles, 
75 mm wide, all round the court, 
including corner pieces; interlocked 
with field tiles and bonded to CC with 
polyurethane / construction adhesive 
at ≤ 300 mm c/c; cut ends of field tiles 
concealed; joint gap ≤ 1 mm. 


Same manufacturer 
as court tiles; PU 
adhesive from an 
approved make (e.g. 
Pidilite / Sika / 
Fosroc) 


Use manufacturer-
compatible edge 
pieces and adhesive. 
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Sr. Material / Work 
Item 


Minimum Recommended 
Specification 


Preferred Brand / 
Manufacturer 


Notes 


9 Court line 
marking 


Two-pack PU / acrylic-PU sports line 
paint over PP-adhesion primer, on a 
cleaned and degreased surface; 
masked, tolerance ±3 mm; 12-month 
durability. Basketball: 50 mm white. 
Volleyball: 50 mm yellow. Badminton: 
40 mm sky-blue. 


Asian Paints / 
Berger / Nippon 
Paint or equivalent 
sports-line system 


Colour layout to be 
approved before 
marking; use a coating 
compatible with PP 
tiles. 


10 Basketball 
stand (pole & 
arm) 


Ground-planted stand, 2 nos. (1 pair): 
100 NB MS pole (about 114 mm OD, 
heavy class, IS 1239 Pt 1, wall ≥ 4.5 
mm); MS tubular cantilever arm 1,500 
mm with brace; rim height 3,050 mm; 
foam pole padding to 2,000 mm; red-
oxide primer and 2 coats synthetic 
enamel or powder coat; MS anchor 
cage; 12-month warranty. Pole centre 
800 mm behind baseline. 


COSCO / Nivia / 
Vector X or 
equivalent 


Submit dimensions, 
wall-thickness 
certificate and finish 
details; to match Drg. 
MSC-01 / 02. 


11 Basketball 
backboard 


1,800 × 1,050 mm, 18 mm BWP / 
marine ply or SMC board in MS angle 
frame; outdoor grade; suitable for ring 
mounting; painted / finished for 
weather resistance. 


COSCO / Nivia / 
equivalent 


Board size and ring 
height as per 
approved layout. 


12 Basketball ring 
& net 


Ring 450 mm dia of ≥ 16 mm steel 
bar, powder-coated / painted, with 12-
loop nylon net. 


COSCO / Nivia / 
Vector X 


Provide durable 
outdoor net with 
secure fixing. 


13 Stand 
foundations & 
collars 


PCC M20 (1:1.5:3) foundation blocks 
600 × 600 × 1,000 mm for each 
basketball stand, with provision for the 
anchor cage; PCC M20 collars 300 × 
300 × 600 mm around post sleeves, 
finished flush with CC; compacted and 
cured. 


Approved cement / 
aggregate 


Foundations to be cast 
and cured before CC 
and tile laying. 


14 Volleyball-cum-
badminton 
posts 


Set of 2 removable posts: 76 mm OD 
GI pipe (≥ 3 mm wall, IS 4736 zinc 
coating), 2,550 mm above court, with 
net winch / tensioner, pulley and 4 mm 
rope; adjustable net heights 1,550 mm 
(badminton), 2,100 mm (junior), 2,240 
mm (volleyball, women); spacing 
8,500 mm c/c; primer + 2 coats 
enamel. 


COSCO / Nivia / 
Vector X or 
equivalent 


One post system to 
serve both volleyball 
and badminton, as per 
estimate. 


15 Ground sleeves MS ground sleeves, bore about 100 
mm, 600 mm deep, with flush cover 
cap; fabricated, primed and painted; 
set in the 300 × 300 collar and finished 
flush with CC. 


Approved fabricator / 
equipment supplier 


Sleeve must be plumb 
and flush; cap to be 
fitted when posts are 
removed. 


16 Sports nets Volleyball net: 1.0 m wide, 100 mm 
mesh, white top band, 9.0 m long, with 
cords. Badminton net: 760 mm wide, 
15–20 mm mesh, white tape top, 9.0 
m long, with cords. Outdoor UV-
resistant nylon / polyester. 


COSCO / Nivia / 
Vector X 


Net dimensions to suit 
the approved court 
layout. 


17 Fasteners / 
anchors 


Hot-dip galvanised or stainless-steel 
fasteners, anchor bolts and 
accessories suitable for outdoor use. 


Hilti / Fischer / 
approved equivalent 


Avoid ordinary 
untreated fasteners in 
exposed locations. 
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Sr. Material / Work 
Item 


Minimum Recommended 
Specification 


Preferred Brand / 
Manufacturer 


Notes 


18 Drainage (U-
drain & soak 
pit) 


Concrete U-drain along the low long 
edge of the court falling to a soak pit 
within school premises, as shown on 
Drg. MSC-02; finished flush with 
surrounding ground and free of 
standing water. 


Approved cement / 
aggregate 


Location and outfall to 
suit site levels; confirm 
scope against the 
estimate before 
execution. 


19 Concrete curing 
/ protection 


Potable water; wet curing for 7 days 
for PCC and CC; curing compound 
only where approved. 


Approved 
construction material 
supplier 


Cure all concrete 
adequately before the 
sports surface is 
installed. 


 


4. Minimum Quality Requirements for PP Sports Surface 


• Material shall be virgin, UV-stabilised polypropylene (PP) copolymer suitable for outdoor sports 
use; no recycled content. 


• Square modules of 250–310 mm with thickness not less than 13 mm, unless the selected 
manufacturer's tested system specifies a thicker equivalent. 


• Tiles shall have positive four-side interlocking connections, an anti-skid textured top and open-
grid drainage, and shall permit individual replacement of damaged tiles. 


• Proposed performance minimums (test reports required): static load ≥ 5 t/sq m; no warping up 
to 70 °C; wet pendulum slip value ≥ 55; shock absorption ≥ 10 %. 


• Tiles shall be suitable for basketball, volleyball and badminton; joint gap ≤ 1 mm; minimum 3-
year manufacturer warranty against fading, cracking, deformation and lock failure. 


• Supplier shall submit product datasheet, warranty, installation instructions and a physical 
sample before procurement. 


• The sports surface shall be installed only after the CC base is cured (7 days), level within ±3 
mm under a 3 m straight-edge, structurally sound and provided with drainage. 


5. Local Availability / Procurement Recommendation 


Common civil-material brands such as UltraTech, ACC and Ambuja are generally available through 
building-material suppliers in Bengaluru and Ramanagara. For specialised PP sports tiles and sports 
equipment, procurement should be made from an authorised manufacturer / dealer able to deliver to 
Ramanagara district and provide installation support, warranty and replacement tiles. As the three 
schools are procured together, a single supplier for tiles, line marking and equipment is recommended 
so that colours, tile modules and spare pieces are consistent across sites. The tender / quotation may 
specify the preferred makes above while allowing "or equivalent" subject to technical approval. 


6. Inspection & Approval Before Purchase 


• Verify manufacturer name, batch / lot details and genuine product documentation. 


• Obtain physical samples of the PP tile (field and edge) and sports equipment for approval. 


• Check colour, thickness, interlock, anti-skid finish and drainage openings of the tile sample; 
obtain test reports for the performance minimums in Section 4. 


• Obtain warranty certificates for sports flooring (3 years) and equipment (12 months). 


• Check cement test certificates, sand / aggregate grading and the thickness of steel pipes (IS 
1239 / IS 4736) before use. 


• Approve the colour layout and line colours on site before marking. 


• Confirm actual availability, delivery lead time and after-sales / service support for Ramanagara. 


• Contractor shall not substitute an approved make without written approval from the project / 
technical representative. 
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7. Important Note 


The attached estimate is a budget estimate and does not prescribe proprietary brands. The brands in 
this report are recommended makes / acceptable reference manufacturers based on product suitability 
and market availability; final selection should be based on approved samples, current local quotations, 
technical compliance and warranty. Rates in the estimate should be retained unless a formal approved 
variation is issued. The estimate excludes felling of trees above 300 mm girth, demolition of structures 
and shifting of services; these would be treated as variations if encountered. 


Prepared for: Model School Project – Bengaluru (Comprehensive School Improvement Program, 
Levi's) 


Proposed Locations: GGHS Ramanagara, KPS Jalamangala & KPS Padarahalli, Bengaluru 


Reference documents: Estimate – Multi-Sport Court, 3 Schools; Drg. MSC-01 and MSC-02 (Rev A, 
06.11.2026) 
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LAYOUT PLAN – MULTI-SPORT COURT (BASKETBALL + VOLLEYBALL + BADMINTON)
Identical for GGHS Ramanagara, KPS Jalamangala and KPS Padarahalli   |   Scale 1:80   |   Dimensions in mm


LEGEND


Blue PP field tiles (colours to be confirmed)


Green – volleyball / badminton zone 15,000 × 7,500


Red – free-throw lanes 3,600 × 3,600 (2 nos.)


Edge / ramp tiles 75 mm wide – all round


Basketball lines – white, 50 mm


Volleyball lines – yellow, 50 mm


Badminton lines – sky-blue, 40 mm


Net line (posts 8,500 c/c)


Foundation / collar below finished level


KEY


1 MS basketball stand, 2 nos.: pole centre 800 behind
baseline, 1,500 arm, rim 3,050


2 PCC M20 foundation 600 × 600 × 1,000 (outside tile edge,
flush with finished ground)


3 Free-throw lane, red, 3,600 × 3,600 with R1,800 arc
(dashed inside lane)


4 Volleyball zone, green, 15,000 × 7,500; net at centre line;
attack lines 2,500 from net


5 Volleyball-cum-badminton posts: 76 OD GI in ground
sleeves, 300 × 300 PCC collars


6 Net line – volleyball net 2,240 / junior 2,100 / badminton
1,550 high


7 Court tiling: 70 × 30 modules of 1 ft (304.8) – grid shown


NOTES


1. Overall size 70 ft × 30 ft = 21,336 × 9,144 (2,100 sqft), including 75
mm edge ramp tiles; perimeter 200 rft.


2. Basketball is a reduced court (20,336 × 8,144) with 500 margin all
round.


3. Where zones overlap, colour precedence is: red lane over green
zone over blue field.


4. Court build-up, drainage (fall 1 in 120 across width), stand and post
details: see Drg. MSC-02.


5. Tile and line colours as per reference photo (FitFlex-type interlocking
PP tiles); final colours to be confirmed.


6. Orientation of long axis (preferably N–S) and exact location to be
fixed at site by the school and engineer.


7. Layout is the same at all three schools; only site levels / drain outfall
differ.


PLAN INDIA
Civil Engineering – Infrastructure & Civil Works


PROJECT


Enhancing Learning Environments: A Comprehensive


School Improvement Program in Bengaluru, Karnataka


(Model School Project – Levi's CSR)


WORK


Development of Multi-Sport Court (Basketball + Volleyball + Badminton)


SCHOOLS (IDENTICAL LAYOUT – 70 ft × 30 ft EACH)


1. GGHS Ramanagara     2. KPS Jalamangala     3. KPS Padarahalli


DRAWING TITLE


LAYOUT PLAN – MULTI-SPORT COURT
Approved layout drawing – to be read with the approved BOQ / Estimate (Multi-Sport Court, 3 Schools)


DRG. NO. SHEET


MSC-01 1 of 2


SCALE DATE STATUS


1:80 06.11.2026 FOR APPROVAL


PREPARED BY CHECKED BY APPROVED BY


Rev A – 06.11.2026 – Issued for approval.   All dimensions in mm unless stated.







A. CIVIL BASE PLAN – CC COURT SLAB, DRAINAGE & FOUNDATIONS (1:120)


FALL 1 IN 120 (about 76 mm across 9,144) TOWARDS SOUTH DRAIN


U-DRAIN 300 wide along south long edge, falling to soak pit


SOAK PIT


3,556 3,556 3,556 3,556 3,556 3,556


21,336


9,
14


4


1


2


1  Stand foundation 600 × 600 × 1,000


    (2 nos., outside tile edge)


2  Post collar 300 × 300 × 600


    (2 nos., flush with CC)


Contraction joints in CC at ≤ 4 m c/c (3,556 × 3,048 panels) – shown dash-dot


B. TYPICAL SECTION A-A – BUILD-UP AT COURT EDGE (1:10)


PP interlocking tile ≥ 13 mm, anti-skid


Edge ramp tile 75 wide, PU-bonded


CC 1:2:4, 50 mm, fall 1 in 120


PCC 1:2:4 (≈ M15), 75 mm


Brick / stone ballast sub-base, 75 mm


Compacted subgrade


Finished ground level


20
0


Excavation 200 below FGL; tile top flush with / ≤ 25 mm above ground


C. VOLLEYBALL-CUM-BADMINTON POST SLEEVE (1:10)


76 OD GI post (cut)


PCC M20 collar


300 × 300 × 600


MS sleeve, 100 bore, 600 deep,


flush cover cap


Finished court level


60
0


E. KEY QUANTITIES PER SCHOOL (as per Estimate)


Court area (excavation, PCC/CC, PP tiles) 2,100 sqft


Edge / side tiles 200 rft


Line marking – 3 sports, multi-colour 1 LS


Basketball stands (pair) 1 pair


Volleyball-cum-badminton post set + nets 1 set


NOTES


1. Excavate 200 below FGL; sub-base, PCC and CC as per BOQ item 1.2 so the tile surface is flush with ground (≤ 25 mm proud).


2. Drain on the low (south) side; outfall to a soak pit within premises – location to suit site levels.


3. Stands and post sleeves are cast before CC is laid; collars finished flush with CC.


4. Stand foundations lie just outside the tiled area (foundation edge meets tile edge).


D. BASKETBALL STAND – SIDE ELEVATION (1:50)


PCC M20 foundation 600 × 600 × 1,000


3,
05


0 
rim


2,
00


0 
pa


dd
in


g


1,
05


0


1,500 arm


Backboard 1,800 × 1,050 (18 mm BWP / SMC)


Ring 450 dia, 12-loop net


100 NB MS pole (≈114 OD)


Pole centre 800 behind baseline
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Terms of Reference (ToR) for Development of Multi-Sport Court (Basketball, Volleyball, Badminton) under Sports Infrastructure facilities in 3 Government Schools under

CSIP Project- Bengaluru



1. Introduction:



Plan International (India Chapter) commonly referred to as Plan India, is an Indian registered not for profit organization that is constantly striving to advance welfare and development for children and equality for all girls and women in India. Through its grassroots social development work, Plan India seeks to create lasting impact in the lives of poor and vulnerable children, their families and communities, by gender transformative child-centered community development


Since 1996, Plan India has improved the lives of millions of children and young people by enabling them to access and benefit from the safety nets and schemes of the government for child protection, quality education and healthcare services, healthy environment, livelihood opportunities and participation in community development. To know more about Plan India, visit www.planindia.org



2. About CSIP- Bengaluru- Rationale for Development of Sports Grounds with Multi-Game Courts



Plan International (India Chapter) is implementing CSIP -Bengaluru project to strengthen education institutions by providing infrastructure facilities in three government schools of GGH-Ramanagar, KPS-Padarahalli and KPS-Jalamangala in the Ramanagar district of Bengaluru South, Karnataka state. The project aims to establish school-based Multi sports play ground in 3 selected government schools under CSIP project in Ramanagar.



To support this vision, Plan India seeks to empanel and engage a qualified agency for the establishment/ Development of Multi-Sport Court (Basketball, Volleyball, Badminton) under Sports Infrastructure facilities in the selected Government schools of GGS-Ramanagar, KPS-Jalamangala and KPS-Padarahalli  in Ramanagar district, Bengaluru South, Karnataka state to promote outdoor sports activities and create inclusive recreational spaces for children, especially girls. The initiative aims to encourage greater participation in sports and physical activities by providing safe, accessible, and well-developed sports court within school premises.


The proposed intervention includes the development of multi-game courts along with interlocking, ground development and allied infrastructure works required to make the sports grounds more functional, accessible, and comprehensive for sports and other school activities. The initiative is designed to create composite recreational spaces that can support multiple outdoor games, school-level activities.

      

     The intervention aims to enhance children’s physical well-being, teamwork, confidence, leadership skills, and active participation in school life through improved access to sports infrastructure.



Goal & Objectives of the Assignment

•	Develop sports ground with multi- sports courts in three schools under program 

· Promote participation of children, especially girls, in outdoor sports and recreational activities. 

· Ground levelling and development works to strengthen sports court 

· Interlocking and allied civil works, marking for improved accessibility and usability.

•	Improve accessibility and usability of sports grounds through interlocking and allied development of multisport court.

· Strengthen opportunities for physical activity, teamwork, leadership, and holistic development among children. 



Deliverables & Timelines

•	Development of sports grounds with multi-sports courts in three schools.

•	Completion of interlocking, ground development, and allied infrastructure works required for functionality and accessibility. 

•	All development works to be completed within the agreed project timeline and in coordination with the respective schools and project team. 

•	All work to be completed by or before 31st December 2026. 



		S. No.



		Activity

		Deliverables

		1st School

		2nd School

		3rd School



		1.

		Establish  Multi sports courts in the following schools 

1. GGH-Ramanagar

2. KPS-Padarahalli 

3. KPS-Jalamangala (Near Primary block school ) as per the BOQs mentioned below with estimated cost for each school.

		[bookmark: _Hlk242709999]Development Multi-Sport Court (Basketball, Volleyball, Badminton) under Sports Infrastructure- facilities.in three government schools with required materials like nets, poles, ground leveling, foundation, flooring, painting/ marking etc. 



		31st Dec’2026

		31st Dec’2026

		31st Dec’2026







Profile and Experience

· Relevant experience in development of sports infrastructure, playgrounds, or multi-game courts in schools or community spaces. 

· Experience in civil works, interlocking, and ground development activities related to recreational infrastructure. 

· Ability to deliver safe, durable infrastructure aligned with project requirements.

· Experience of working with schools, educational institutions, or community-based infrastructure projects will be preferred.

· Preference will be given to vendors/agencies with prior experience in the development of multi-sport grounds in the educational institutions 



Proposal Submission Requirements



· Interested and experienced vendors/agencies are required to submit the following documents as part of their proposal:

· Technical proposal outlining the Implementation/ work plan, approach,

and timelines for establishment of sports courts.

Detailed financial proposal with item-wise cost breakup, including equipment, installation, logistics, and applicable taxes

· Organizational profile, including details of relevant experience, technical expertise, and key personnel/team members proposed for implementation across the 3 schools

· Portfolio/sample reports, photographs, case studies, or completion documents of similar assignments undertaken in schools, preferably in Bengaluru or with government schools/CSR-supported projects

[bookmark: _GoBack]

Budget and Payment



•	The agreement will be milestone-based, and payments will be released upon successful completion and verification of agreed deliverables and satisfactory progress of work

•	Payment milestones will be linked to key deliverables such as inception meeting, Multi sport ground establishment, submission of required reports/documentation 

•	All payments will be processed in accordance with organizational financial policies and submission of valid invoices and supporting documents

•	Applicable taxes and statutory deductions will be made as per prevailing rules and regulations



Safeguarding Policy:

  
Plan is committed to protect children and to prevent them from any harm they may be exposed to through our work. Therefore, the successful candidate will be requested to sign and comply with Plan India’s safeguarding policy and will comply to all the standards of research that has been enlisted under it. Level of Contact as per the safeguarding policy is ‘DIRECT’ – LEVEL OF CONTACT ‘A’.
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Summary Classroom Renovation

				SUMMARY SHEET B3:D14

				Estimated Cost for Classroom Civil work, Electrical repair & BaLA painting under Classroom Renovation budget head 

				Project Name - Comprehensive School Improvement Program – Bengaluru (Levi's)

				Name of Work - Classroom Renovation Civil work, Electrical repair & BaLA painting

				Name of Schools - GGHS Ramanagara, KPS Jalamangala and KPS Padarahalli

				Sr.No.		Activity 		Amount

				1		GGHS RAMANAGARA

				1.1		Classroom Renovation (6 Nos.) -
Minor civil repairs, plaster repair, interior painting (Excluding GST)

						Total Estimated Cost for Minor civil repairs, plaster repair, interior painting                            (Including 18% GST)

				1.2		Classroom Renovation (6 Nos.) -
Electrical wiring, light, fan repairs, MS door at terrace, school building earthing & Safety MS Grill to corridor parapet 1st & 2nd floor of school building (Excluding GST)

						Total Estimated Cost for Electrical wiring, light, fan repairs, MS door at terrace, school building earthing & Safety MS Grill to corridor parapet 1st & 2nd floor of school building. (Including 18% GST)

				1.3		Classroom Renovation (6 Nos.) -
Educational BaLA or Mural painting to improve the classroom environment.                          (Excluding GST)

						Total Estimated Cost for Educational BaLA or Mural painting to improve the classroom environment. (Including 18% GST)



				2		KPS JALAMANGALA

				2.1		Classroom Renovation (2 Nos.) -
Minor civil repairs, plaster repair, interior painting (Excluding GST)

						Total Estimated Cost for Minor civil repairs, plaster repair, interior painting                            (Including 18% GST)

				2.2		Classroom Renovation (2 Nos.) -
Electrical wiring, light, fan repairs (Excluding GST)

						Total Estimated Cost for Electrical wiring, light, fan repairs. (Including 18% GST)

				2.3		Classroom Renovation (5 Nos.) -
Educational BaLA or Mural painting to improve the classroom environment.                          (Excluding GST)

						Total Estimated Cost for Educational BaLA or Mural painting to improve the classroom environment. (Including 18% GST)



				3		KPS PADARAHALLI

				3.1		Classroom Renovation (5 Nos.) -
Educational BaLA or Mural painting to improve the classroom environment.                          (Excluding GST)

						Total Estimated Cost for Educational BaLA or Mural painting to improve the classroom environment. (Including 18% GST)





						TOTAL COST FOR CLASSROOM RENOVATION - CIVIL WORK, ELECTRICAL REPAIR & BaLA PAINTING IN 3 SCHOOLS (INCLUDING GST)





GGHS Ramanagara ClassroomRepair

		BILL OF QUANTITIES (BOQ)

		Classroom Renovation Civil work, Electrical repair & BaLA painting (6 Nos. of Classrooms)

		Government Girls High School (GGHS), Ramanagara, Bengaluru, Karnataka



		1.1   Classroom Renovation (6 Nos.) - Minor civil repairs, plaster repair, interior painting

		Classrooms 1, 2, 3 & 4 - 4 Nos. (each: 8.8m x 6.9m x 3m; 1 door 1.3x2.4m; 3 windows 1.8x1.5m each)                                       Classroom 5,6 - 2 Nos. (each: 14.15m x 6.9m x 3m; 1 door 1.3x2.4m; 7 windows 1.8x1.5m each)

		S.No		Item Description		Unit		Qty		Rate 		Amount 

		1		Dismantling of existing damaged door with frame, incl. removal of debris		Nos		6

		2		Supply & fixing new flush door (35mm) with wooden/steel frame, hinges, tower bolt, handle & lock, size 1.3m x 2.4m, complete		Nos		6

		3		Dismantling of existing damaged window with frame, incl. removal of debris		Nos		26

		4		Supply & fixing new UPVC window with glass, mosquito mesh & fittings, size 1.8m x 1.5m per window, complete (Windows - 26 Nos.)		sqm		70.2

		5		Minor plaster & tile patch repair to walls (cracks, damaged patches)		sqm		50

		6		Wall surface preparation & 2 coats premium acrylic emulsion paint (above dado) - 4 Nos. of Classrooms (Area - 120 sqm per room)		sqm		480

		7		Wall surface preparation & 2 coats premium acrylic emulsion paint (above dado) - 2 Nos. of Classrooms (Area - 165 sqm per room)		sqm		330

		8		Dark dado painting (2 coats enamel/weather-coat, up to 3ft height from floor) - 4 Nos. of Classrooms (Area - 28 sqm per room)		sqm		112

		9		Dark dado painting (2 coats enamel/weather-coat, up to 3ft height from floor) - 2 Nos. of Classrooms (Area - 37 sqm per room)		sqm		74



		Sub-Total (1.1)

		Add: GST @ 18%

		Grand Total (Rounded)





		1.2   Classroom Renovation (6 Nos.) - Electrical wiring, light, fan repairs, MS door at terrace, school building earthing & Safety MS Grill to corridor parapet 1st & 2nd floor of school building

		S.No		Item Description		Unit		Qty		Rate 		Amount 

		1		Electrical repair - concealed PVC conduit rewiring, new switch/DB board per classroom		Room		6

		2		Supply & fixing new LED tube light/batten fixture (20W), complete		Nos		28

		3		Ceiling fan repair/rewinding & rebalancing, or replacement where damaged		Nos		16

		4		Providing & fixing new MS fabricated door at terrace headroom - MS angle frame (40x40x6mm), MS sheet/grill shutter, heavy-duty hinges, locking arrangement, 2 coats primer + 2 coats enamel paint.           Size: 1.2m x 1.95m		Sqm		2.34

		5		Earthing - Providing electrical earthing to school building (G+2) as per IS:3043 GI pipe earthing pits with masonry chamber, CI cover, salt & charcoal treatment		Nos		4

		5(a)		Earthing - GI strip (25x5mm) earthing connection/riser from pits to floor-wise distribution boards, incl. clamps & fixing		Rm		80

		5(b)		Earthing - Testing, commissioning & earth resistance measurement		LS		1

		6		MS fabrication safety grill to corridor parapet, 1st & 2nd floor - MS square tube posts (25x25x3mm), top/bottom rail, vertical infill bars @ 100-125mm c/c (child-safe spacing), height 1m, incl. painting		Rm		80



		Sub-Total (1.2)

		Add: GST @ 18%

		Grand Total (Rounded)





		1.3 Classroom Renovation (6 Nos.) - Educational BaLA or Mural painting to improve the classroom environment.    

		S.No		Item Description		Unit		Qty		Rate 		Amount

		1		BaLA/Mural theme painting — educational wall art, multi-color, complete		sqm		60

		Sub-Total (1.3)

		Add: GST @ 18%

		Grand Total (Rounded)





		Combined Summary

		Sub-Total (1.1+1.2+1.3)

		Add: GST @ 18%

		Grand Total (Rounded)





KPS Jalamangala ClassroomRepair

		BILL OF QUANTITIES (BOQ)

		Classroom Renovation civil work, Electrical repair & BaLA painting (5 Nos. of Classrooms)

		Karnataka Public School (KPS) Jalamangala, Bengaluru, Karnataka



		2.1   Classroom Renovation (2 Nos.) - Minor civil repairs, plaster repair, interior painting

		Classroom 1 - 1 Nos. (each: 6m x 6m x 3m; 1 door 0.9x2.1m; 4 windows 1.5x1.2m each)                                                    Classroom 2 - 1 Nos. (each: 10m x 6m x 3m; 1 door 1.2x2.1m; 6 windows 2x1.2m each)

		S.No		Item Description		Unit		Qty		Rate 		Amount 

		1		Supply & fixing new flush door (35mm) with wooden/steel frame, hinges, tower bolt, handle & lock, size 1.3m x 2.4m, complete		Nos		2

		2		Minor plaster & tile patch repair to walls (cracks, damaged patches)		sqm		30

		3		Wall surface preparation & 2 coats premium acrylic emulsion paint (above dado) - 1 Nos. of Classroom Primary (Area - 81 sqm per room)		sqm		81

		4		Wall surface preparation & 2 coats premium acrylic emulsion paint (above dado) - 1 Nos. of Classrooms Secondary (Area - 116 sqm per room)		sqm		116

		5		Dark dado painting (2 coats enamel/weather-coat, up to 3ft height from floor) - 1 Nos. of Classrooms Primary (Area - 21 sqm per room)		sqm		21

		6		Dark dado painting (2 coats enamel/weather-coat, up to 3ft height from floor) - 1 Nos. of Classrooms Secondary (Area - 28 sqm per room)		sqm		28



		Sub-Total (2.1)

		Add: GST @ 18%

		Grand Total (Rounded)





		2.2   Classroom Renovation (2 Nos.) - Electrical wiring, light, fan repairs

		S.No		Item Description		Unit		Qty		Rate 		Amount 

		1		Electrical repair - concealed PVC conduit rewiring, new switch/DB board per classroom		LS		1

		2		Supply & fixing new LED tube light/batten fixture (20W), complete		Nos		10

		3		Ceiling fan repair/rewinding & rebalancing, or replacement where damaged		Nos		3





		Sub-Total (2.2)

		Add: GST @ 18%

		Grand Total (Rounded)





		2.3 Classroom Renovation (5 Nos.) - Educational BaLA or Mural painting to improve the classroom environment.    

		S.No		Item Description		Unit		Qty		Rate 		Amount

		1		BaLA/Mural theme painting — educational wall art, multi-color, complete		sqm		70

		Sub-Total (1.3)

		Add: GST @ 18%

		Grand Total (Rounded)



		Combined Summary

		Sub-Total (2.1+2.2+2.3)

		Add: GST @ 18%

		Grand Total (Rounded)





KPS Padarahalli ClassroomRepair

		BILL OF QUANTITIES (BOQ)

		Classroom Renovation -  BaLA painting (5 Nos. of Classrooms)

		Karnataka Public School (KPS) Padarahalli, Bengaluru, Karnataka



		3.1 Classroom Renovation (5 Nos.) - Educational BaLA or Mural painting to improve the classroom environment.    

		S.No		Item Description		Unit		Qty		Rate 		Amount

		1		BaLA/Mural theme painting — educational wall art, multi-color, complete		sqm		70

		Sub-Total (3.1)

		Add: GST @ 18%

		Grand Total (Rounded)



		Summary

		Sub-Total (3.1)

		Add: GST @ 18%

		Grand Total (Rounded)






